Proposed Practicum Workplan- Family Treatment Center (Project planner)                 Jan 3- April 11/2012                            Dori Gaudet

| Deliverables | Tasks | Timeline | Partnership/ consultant |
| --- | --- | --- | --- |
| Partnership Development |  |  |  |
| Identify and connect with Ministry contact/ consultant | Email/ phone introduction Request any best practice information and relevant evidence based research Potential Advisory members/consultant Other? | Completed | Brett/ Chuck/Patti Copy of Provincial ADS model for Saskatchewan Crystal Nievadomy – Ministry of Health Rep |
| Engage Advisory Committee | Gather potential list of members Draft letter of introduction and proposed involvement in project Coordinate meeting/ telehealth/ teleconference with members | Completed | Brett/ Chuck / Patti Ministry consultant Current list of advisory committee members- chuck Terms of reference for committee? |
| Focus Groups | Engage focus staff that can assist with engaging potential clients for focus groups. What do we want to know? Proposal refers to focus groups for involvement of children in programming, for children, education and recreation for children. What else do we want to know? Organize and facilitate session- who does this? Collect data and implement information into programs | Completed | Has this been started? no ADS staff Maria Lloyd, Caroline V, Jennifer S/ STD clinic Consult Colleen D for questionnaire or process Potential Clients- DEW/ weekly support Facilitator- hire a facilitator or use existing groups through staff Share results with Advisory for feedback |
| Partnership development with other regions and referral sources. | Make contact with regions ( ADS to start) Provide information. Re: program, first intake, Referral information and processes. Develop referral package for distribution to RED for dissemination | June 2012- Dec 2012 completed | RD table Front line ADS contacts Other? Prepare presentation for RED table and PAPHR board |
| Program/ Procedure Development |  |  |  |
| Admission criteria | Develop Draft admission criteria Review with stakeholders Implement changes and Finalize document | completed | Reference proposal |
| Admission processes/ procedures | Develop Draft admission process doc Review with stakeholders Implement changes and Finalize doc Checklist and forms | completed | Reference proposal Calder Centre Bridgepoint |
| Admission form Must include: cognitive ability, court involvement, criminal history, MH issues, physical health, child information, child protection issues | Develop Draft admission form Review with stakeholders Implement changes and Finalize doc | completed | Reference proposal Calder Centre Bridgepoint |
| Referral process | Develop Draft referral process doc Review with stakeholders Implement Changes and Finalize document | completed | Reference proposal Calder Centre Bridgepoint |
| Assessment Form | Develop Draft admission form Review with stakeholders Implement changes and Finalize doc | completed | Reference proposal Calder Centre Bridgepoint |
| Assessment process/procedure | Develop Draft admission form Review with stakeholders Implement changes and Finalize doc | completed | Reference proposal Calder Centre Bridgepoint |
| Client Orientation package | Develop Draft Client orientation pkg Review with stakeholders Implement changes and Finalize doc | completed | Reference proposal Calder Centre Bridgepoint |
| Programming |  |  |  |
| Treatment Program | Research best practice programming for Mom’s/ Children Make recommendations on treatment program | completed | Jean tweed Stephanie Covington Peardonville House |
| Case Management Protocols | Research best practice Draft CM protocols Review with stakeholders Implement changes and finalize document | completed | Reference best practice guidelines ABI manual |
| Engage School Division re: Classroom in Family treatment Centre | 1 FTE teacher and Educational Assistant Potential partnership with C&Y ward as referenced in proposal documents Initiate contact/ meetings | Jan 2012- completed | Sask. Rivers School Division Brett/ Chuck/ Patti/ Ward classroom Calder- on site schooling Draft Letter |
| Daycare Plan | Become informed re: RFP process and successful candidate Work with service provider to develop and implement plan/ processes and procedure Get licensed Daycare list Meet with Buds in Bloom Daycare RFP from Doug Dahl | Jan 2012 completed | Successful RFP applicant- Family Futures? Brett/ Chuck/ Patti Ministry consultants? |
| Human Resource Development |  |  |  |
| Develop Staffing Model | Determine reporting structure, classification, JD and union affiliation for all positions. Write Draft Job description using region/ SAHO process for positions to be reviewed and ready for posting Prepare positions for posting on SHAREPOINT so they are ready to go when needed. | completed | Regional Recruitment and Retention Department SAHO Brett/ Chuck/ Patti. |
| Incident reporting/guidelines | Consult OH&D Ensure process and procedure match regional policy Gather proper forms/ policies etc Develop protocol for staff in centre | completed | PAPHR- OH&D department PAPHR policy manual |
| Draft letter to SAP | Childcare maintained in home community Housing maintained in home community | completed | Draft letter for Brett to Ministry of Social Assistance. |
| Intake Process | Must include lice and bed bug process | completed |  |
| Plan to facilitate Methadone | Set meeting to develop protocol | In progress | Detox, Dr. L. Lanoie, pharmacy, nurse position |